## Slide 1: What works for fostering step-down?
Lessons learned from step-down models and good practice features for managing delivery

## Slide 2: Acknowledgements
We would like to thank those involved in providing valuable contributions to this research including from:
  The Big Fostering Partnership
  Lancashire County Council
  The Mulberry Bush School
  Birmingham Children’s Trust
  Government Outcomes Lab (GoLab), University of Oxford
  Cheshire’s Fostering Better Outcomes
  DN2 STARS Partnership

## Slide 3: Introduction

## Slide 4
    This report was produced as part of an evaluation of the Big Fostering Partnership (BFP) undertaken on behalf of Staffordshire County Council (the lead authority for the partnership across seven areas). The BFP project was designed to provide specialist fostering arrangements for children and young people currently living in residential children's homes. Delivered over four years, it was funded through a Social Impact Bond (SIB) with Big Issue Invest Ltd providing social finance and National Fostering Group (NFG) as the delivery arm, also accessing funding via the Life Chances Fund (LCF).
    As part of the evaluation, York Consulting LLP (YCL) undertook this additional research to identify good practice and learning insights regarding the delivery of step-down interventions and the Social Impact Bond (SIB) approach to financing and managing similar children’s social care initiatives.
    In the following we set out a series of good practice features or lessons learnt, drawing on illustrative examples across several local authority models.

## Slide 5: What works well for fostering step-down?
Step-down delivery models are designed to facilitate the transition of children and young people (CYP) from residential care to family foster placements. These models aim to provide a structured and supportive process that addresses the unique needs of each child, ensuring a smooth and successful transition. Various local authorities (LA) have implemented different step-down delivery models.
This section considers what has worked well for residential step-down interventions/projects in other LA areas and includes case study examples, providing valuable insights to consider when designing future step-down interventions.

## Slide 6: Strong stakeholder engagement
  Strong stakeholder engagement is essential for the success of step-down fostering projects. Engaging all relevant stakeholders, including social workers, carers, and placement professionals, early and continuously throughout the project is vital for ensuring a coordinated and collaborative approach.
              Case Study: Lancashire
    Lancashire developed several best practices to enhance matching outcomes through strong stakeholder engagement.
    Social workers, residential key workers, and therapists presented cases in 15-minute slots during meetings, bringing the child’s profile to life for fostering agencies.
    Engaged the right representatives from agencies, such as regional managers who understand carer skill sets, significantly improving matching outcomes.
    Weekly calls with providers, including Friday summary updates, kept step-down children on their radar, ensuring placements remained a priority.

## Slide 7: Senior-level buy in
  Achieving senior-level buy-in is particularly crucial for securing the necessary support and resources for a project.
              Case Study: Fostering Better Outcomes
  Strong buy-in and ownership from key stakeholders, including the commissioner, senior leaders, and the project manager, were pivotal for the success of Fostering Better Outcomes in Cheshire.
  This buy-in ensures that the project has the backing it needs to succeed and that all necessary resources are allocated to support the placements.

## Slide 8: Dedicated roles and responsibilities
    Having dedicated teams and roles, such as a strong project manager focused solely on foster care searches, helps streamline the process and improve outcomes.
              Case Study: Lancashire
    Dedicated brokerage and family finding teams in Lancashire, for example, played a critical role in identifying suitable placements and supporting the transition. These teams ensure that the process is efficient and that the best possible matches are made for the children.
              Case Study: DN2 Stars
    As part of an evaluation of the DN2 STARS programme, York Consulting found that the service model worked well; the key worker approach was clearly valued by parents and carers, offering them a dedicated practitioner to listen to their needs, provide reassurance and advice, and advocate to other professionals for their and their child’s needs.
    The multi-disciplinary progress meetings and therapeutic parenting training were also valued enablers of positive outcomes.

## Slide 9: Structured assessments
    Ensuring structured assessments are in place to evaluate children’s readiness for transition from residential care to foster care is integral.
    Tools like the BERRI system are instrumental in evaluating children's readiness for transition from residential care to foster care or returning to their families. The BERRI system, for instance, provides detailed reports and therapeutic assessments, which support decision-making and reduce wait times for Child and Adolescence Mental Health Services (CAMHS) by up to 18 months.
    These structured assessments ensure that the needs of the children are thoroughly understood and addressed, facilitating a smoother transition. By providing a clear and comprehensive understanding of each child's needs, the right support is in place from the outset.
    For residential step-down, placements with newer carers or in environments unsuitable for the children’s needs can lead to disruptions. A process to fully understand children’s needs and review whether carer matches are suitable in these circumstances is crucial for the success of the placements.

## Slide 10: Appropriate therapeutic support
    One critical success factor is having appropriate therapeutic support for both the child and the foster family. Therapeutic support can include a range of services, such as individual therapy for the child, family therapy, and support groups for carers. These services help address any underlying issues that may affect the child's ability to adjust to a new placement and provide ongoing support to both the child and the carers.
              Case Study: Birmingham Children’s Trust and the BERRI System
  The BERRI system provides therapeutic support services, including assessments for conditions such as ASD and ADHD.
  Key practices:
    Regular reassessments every three months ensure placement decisions are based on up-to-date information.
    The BERRI consultation process tailors transition recommendations to individual needs, ensuring moves occur at the right time with necessary support.

## Slide 11: Streamlined and consistent transition
Financial limitations often impact the ability to provide adequate transition periods. Future projects should factor these transition periods into their budgeting to ensure smoother transitions for children.
              Case Study: DN2 STARS
  One critical success factor identified in the DN2 STARS evaluation was the consistency of the young person’s support offer. One of the changes made to the STARS programme during delivery was expanding the peer mentor support available so that young people in all cohorts could have the same level of support. Given the range of challenges young people in care or on the edge of care face, future support programmes taking a similar approach should consider providing dedicated support for all young people open to the programme, so that support can be effectively tailored to meet young people’s needs from the outset, regardless of their care status.

## Slide 12: Flexibility in contracts
              Case study: Lancashire’s approach to step-down
    Lancashire trialled a dedicated contract structured as a soft block arrangement.
    Flexibility: they purchased a set number of foster carers from an agency, reserving them specifically for step-down children. If a match was not made, they had the flexibility to release the carer and look for another.
    This type of contract proved effective for several years and was later integrated into the broader fostering contract.
    Transition process: Included a four-stage transition process, moving from intensive overnight stays as an introduction to a full placement while ensuring support gradually reduces. However, this reduction in support was tailored to the YP and flexible.
              Case study: Cheshire’s Fostering Better Outcomes (FBO)
    Initially sourced carers solely through Foster Care Associates (FCA) but later developed relationships with six additional fostering agencies to widen the pool of potential carers.
    This approach led to successful placements, such as placing a young person through a non-FCA agency.
    Required significant effort to establish partnerships but ultimately streamlined the process for sourcing potential carers.

## Slide 13: Good practice features: organising & managing delivery
Lessons for SIB partnerships:
Social Impact Bonds (SIBs) are a model for organising and delivering public services, bringing together commissioners (such as local government), service providers and investors. SIBs intend to improve social outcomes for beneficiaries and there is upfront investment, offering capital to deliver positive social impact where resources might be otherwise constrained. SIBs are also performance based, relying on successful and measurable outcomes.
The following learning may be valuable when considering future arrangements in social care projects.

## Slide 14: The Life Chances Fund
  The LCF evaluation by the Government Outcomes Lab offers insights into using SIBs for social care projects. These projects followed a performance-based funding model, tying payments to outcomes like placement stability and improved child well-being. The aim was to transition children from residential care to family-based foster care, enhancing life outcomes and achieving cost efficiencies.
  Challenges included extended timelines and intricate negotiations among multiple stakeholders. SIBs also required substantial time and expertise to design contracts, establish outcome metrics, and align interests.
  However, the evaluation indicates that there were several facilitators within the development processes:
  Top-up funding: Development grants from the LCF acted as a hook, perceived as risk underwriting by the government, and funded early-phase external support.
  Operational preparedness: Social investment fund managers provided new insights.
  Creative procurement: Trust-based working and early market engagement fostered collaboration.
  High-quality services: Ambition to deliver additional services with clear specifications.
  Technical expertise: Consultants and peers contributed to financial modelling and application development.
  There was a strong call to simplify SIBs through easy-to-use templates, better technical guidance, and streamlined application processes. Local commissioners expressed a desire to build in-house expertise to reduce reliance on external support.
Notes: The use of social impact bonds in children's care: main research report, 2021, Government Outcomes Lab

## Slide 15: The Essex Edge of Care SIB
              Programme overview
    Aimed to improve outcomes for adolescents at risk of going into care between 2013 - 2018.
    Commissioned by Essex County Council and funded by a group of social investors with several delivery partners.
    Intervention: intensive family-based and evidence-based intervention, Multisystemic Therapy (MST).
              Good practice:
    Test and Learn approach: Flexible resources and outcome-focused structure enabled development and testing of adaptations.
    Adequate mobilisation period: Recruitment delays highlighted the need for an expert programme manager with clinical MST experience.
    Investment in staff and training: Prioritised recruiting best practice leaders, high-quality therapists, supervisors, and programme managers. Included team management incentives and training in MST in the US and Europe.
    Therapist in waiting: Added flexibility and bridged service gaps due to sickness or leave, contributing to efficient team culture.
    Flexible Innovation Fund: Allowed rapid removal of barriers for families, improving engagement.
    Integrated referral routes: Effective referral routes across children's services and youth offending services mitigated exclusion risks.
    Payment mechanism: Saved on frequency measure of care days avoided, encouraging consistent effort across the cohort.
Notes: Essex-Edge-of-Care-final-report.pdf, 2021, Social Finance

## Slide 16: Positive Families Partnership SOC
              Programme overview
    Aimed to support young people aged 10 to 16 in London to prevent them from entering care, facilitated by the Greater London Authority (GLA).
    Interventions: Family therapies like MST and Functional Family Therapy (FFT).
    Social Outcomes Contract (SOC) vs. SIB: SOCs focus on improving delivery and management of established interventions, while SIBs often finance and test new interventions. Both involve payment for outcomes and investment from social investors.
    SOCs emphasise reducing risk and enhancing performance through collaboration.
              Good practice from this SOC
    Early buy-in from commissioners and operational staff: Facilitated by the GLA, securing early buy-in encouraged discussions and early decision-making, fostering collaboration and commitment. Ongoing engagement helped maintain support from operational staff despite high turnover in some boroughs..
    Simplicity in payment mechanisms: Keeping outcomes payments simple helped communicate the SOC's purpose clearly to all stakeholders, ensuring alignment with project goals.
    Role of lead commissioner: Initially LB Tower Hamlets, later LB Sutton, streamlined development and management processes, creating efficiencies in commissioning and contract management.
    Diverse providers: Involvement of providers with different expertise and geographic coverage enhanced service delivery quality.
    Clear communications and processes: Open forums, regular meetings, and ongoing strategic and operational boards ensured transparency and engagement, maintaining momentum and addressing challenges.
    Co-commissioning: Offered opportunities for scale and efficiency but required thorough needs analysis and infrastructure development. The collaborative agreement among boroughs provided a scalable model for incorporating new boroughs.
Notes: Positive Families Partnership Social Outcomes Contract: An Indepth Review, 2021, Government Outcomes Lab

## Slide 17: Overall lessons from other SIB partnership models regarding effective commissioning, management, and delivery:
  Clear specifications and ambitious goals
        Successful SIB projects have had clear specifications and ambitious goals, ensuring that all parties are aligned and working towards common objectives.
  Operational preparedness
        Where SIB projects have been most effective, they have demonstrated strong operational preparedness, often with external consultants or social investment fund managers bringing new insights and expertise.
        Access to technical expertise has been crucial for financial modelling and developing SIB/ funding applications.
  Creative procurement approaches
        Trust-based working and early market engagement have been beneficial in procurement processes, fostering collaboration and innovation.
  Simplified processes
        Simplifying SIB processes through easy-to-use templates, better technical guidance, and streamlined application processes has been recommended to reduce complexity and improve efficiency. Similarly, having simple payment processes avoids overcomplicating the mechanisms, especially in an already complex landscape.

## Slide 18: Acknowledgements
We would like to thank those involved in providing valuable contributions to this research including from:
  The Big Fostering Partnership
  Lancashire County Council
  The Mulberry Bush School
  Birmingham Children’s Trust
  Government Outcomes Lab (GoLab), University of Oxford
  Cheshire’s Fostering Better Outcomes
  DN2 STARS Partnership

## Slide 19: Thank You
Georgina Cowen
Partner, York Consulting
Nelly Jones
Consultant, York Consulting